## Summary
Field | Value
Document | Sandbox Payment Gateway Test Case Checklist
Project | VromonBilash Resort/Package Booking
Environment | Payment Sandbox / QA only
Total test cases | 42
Execution status | Not Run - checklist ready for execution
Payment safety | Use provider test cards/methods only; no real card data
Exit criteria | No P0/P1 open defect; success/failure/cancel/webhook reconciliation passed
Required evidence | Request/response IDs, gateway transaction ID, booking ID, webhook payload, screenshots, logs

## Test Case Checklist
TC ID | Area | Test Case | Preconditions | Steps | Test Data | Expected Result | Priority | Type | Status | Actual Result
PAY-001 | Configuration | Sandbox credentials and merchant config | Sandbox access available | Verify merchant ID, secret/config, currency, callback URLs and environment flag. | Sandbox merchant config | No production endpoint/credential; config loads successfully. | P0 | Setup | Not Run
PAY-002 | Configuration | HTTPS and callback allowlist | Sandbox deployed | Verify redirect, success, failure, cancel and webhook URLs. | Approved URLs | TLS valid; URLs resolve; no localhost/production mixing. | P0 | Integration | Not Run
PAY-003 | Configuration | Currency and amount precision | Checkout total available | Create checkout for whole and decimal amounts. | BDT 2000; BDT 2000.50 | Gateway amount/currency match server checkout exactly. | P0 | Functional | Not Run
PAY-010 | Success | Successful card payment | Valid sandbox checkout and success test card | Open checkout; pay with success method; return to merchant. | Provider success card | One successful transaction; booking Paid/Confirmed; receipt/reference shown. | P0 | E2E | Not Run
PAY-011 | Success | Successful mobile wallet payment | Wallet sandbox enabled | Pay with wallet success method. | Provider success wallet | Payment and booking status synchronized; correct amount. | P0 | E2E | Not Run
PAY-012 | Success | Success callback after redirect | Payment initiated | Complete success; inspect redirect and webhook. | Success transaction | Server trusts verified callback/webhook; UI and backend agree. | P0 | Webhook | Not Run
PAY-013 | Success | Receipt and confirmation notification | Successful payment | Check email/SMS/in-app receipt. | Valid QA contact | Receipt contains correct booking ID, amount, currency and masked payment reference. | P1 | Notification | Not Run
PAY-014 | Success | Success refresh/back/duplicate click | Successful payment page | Refresh and use browser back/forward; click Pay twice rapidly. | Same transaction | No duplicate charge or booking; status remains Paid. | P0 | Idempotency | Not Run
PAY-020 | Failure | Generic gateway decline | Sandbox checkout | Use decline test card/method. | Provider decline card | Payment Failed; booking not Paid; actionable error; retry available. | P0 | Negative | Not Run
PAY-021 | Failure | Insufficient funds | Sandbox checkout | Use insufficient-funds method. | Provider insufficient-funds card | No booking confirmation; no false success; transaction reason mapped safely. | P1 | Negative | Not Run
PAY-022 | Failure | Invalid card details | Payment form open | Enter invalid number/expiry/CVV. | Invalid test values | Client/server validation; no gateway charge; sensitive input not logged. | P0 | Validation | Not Run
PAY-023 | Failure | Expired card | Payment form open | Use expired test card. | Provider expired-card method | Clear failure; no booking/payment success. | P1 | Negative | Not Run
PAY-024 | Failure | 3DS/authentication failure | 3DS sandbox enabled | Trigger failed/incorrect authentication. | Provider 3DS failure method | Payment fails or remains unpaid; retry supported; no duplicate. | P0 | Security | Not Run
PAY-025 | Failure | Gateway 5xx/timeout | Fault injection or provider method | Simulate gateway timeout/5xx. | Timeout/failure fixture | Safe Pending/Failed state; no false Paid; retry/reconciliation path. | P0 | Resilience | Not Run
PAY-026 | Failure | Client disconnect after submit | Payment submitted | Disconnect network before response; reconnect and refresh. | QA network profile | Final status recoverable by polling; retry does not double charge. | P0 | Resilience | Not Run
PAY-030 | Cancel | Cancel at payment page | Payment page open | Click gateway Cancel/Back. | Sandbox cancel | Transaction Cancelled/Pending; booking unpaid; retry option shown. | P0 | Negative | Not Run
PAY-031 | Cancel | Cancel after 3DS prompt | 3DS sandbox | Cancel during authentication. | 3DS cancel method | No Paid status; no duplicate callback effects. | P1 | Negative | Not Run
PAY-032 | Cancel | Merchant cancel callback | Cancel flow configured | Cancel and inspect callback payload. | Cancel transaction | Callback authenticated and maps to correct booking/transaction. | P0 | Webhook | Not Run
PAY-040 | Amount | Tamper amount in browser request | QA account and sandbox | Change amount/currency/order ID before submit. | amount=1; altered order ID | Server rejects/recalculates using trusted checkout; no underpayment. | P0 | Security | Not Run
PAY-041 | Amount | Tamper booking/user ownership | Two QA users | Replace booking/order ID with another user’s ID. | User A token + User B order | Authorization rejects; no cross-user payment or data exposure. | P0 | Authorization | Not Run
PAY-042 | Amount | Coupon/discount mismatch | Valid coupon fixture | Apply/change coupon after checkout; submit payment. | Valid/expired coupon | Server recalculates discount; amount shown and charged match. | P0 | Business Rule | Not Run
PAY-043 | Amount | VAT/service charge mismatch | Tax fixture configured | Compare checkout, gateway and receipt totals. | VAT/service charge values | Sub-total + discount + VAT/fees = charged total. | P0 | Business Rule | Not Run
PAY-044 | Amount | Zero/negative/very large amount | Validation endpoint available | Attempt amount 0, negative and max boundary. | 0, -1, max integer | Rejected safely; no gateway request for invalid amount. | P1 | Boundary | Not Run
PAY-050 | Webhook | Valid webhook signature | Webhook endpoint available | Send provider-signed success webhook. | Valid signature | Accepted once; transaction/booking updated. | P0 | Security | Not Run
PAY-051 | Webhook | Invalid signature | Webhook endpoint available | Send modified/unsigned webhook. | Invalid signature | Rejected; no payment/booking status update. | P0 | Security | Not Run
PAY-052 | Webhook | Replay same webhook | Successful webhook recorded | Send identical webhook twice. | Same event ID | Idempotent; one status transition; no duplicate receipt/booking. | P0 | Idempotency | Not Run
PAY-053 | Webhook | Out-of-order webhook | Events supported | Send failed then success, or success then pending in wrong order. | Event sequence | State machine prevents invalid downgrade/false final state. | P0 | State | Not Run
PAY-054 | Webhook | Unknown transaction/order ID | Webhook endpoint available | Send valid signature for unknown ID. | Unknown reference | Safe 4xx/ignored with alert; no unrelated data change. | P1 | Negative | Not Run
PAY-055 | Webhook | Malformed webhook payload | Webhook endpoint available | Remove required fields/change types. | Malformed JSON/schema | Validation error; no partial update; alert/log correlation. | P1 | Validation | Not Run
PAY-060 | Reconciliation | Gateway success but booking update fails | Fault injection | Force booking DB/API failure after payment success. | QA failure fixture | Reconciliation queue/alert; no silent orphan charge; retry safe. | P0 | Recovery | Not Run
PAY-061 | Reconciliation | Booking success but gateway unknown | Fault injection | Return unknown gateway result after booking attempt. | Unknown status | Booking not marked Paid until verified; pending/reconciliation state. | P0 | Recovery | Not Run
PAY-062 | Refund full amount | Paid sandbox transaction | Trigger full refund. | Provider refund method | Refund ID/status stored; booking/refund status correct; notification sent. | P1 | Refund | Functional | Not Run
PAY-063 | Refund partial amount | Paid sandbox transaction | Trigger partial refund. | Partial refund amount | Partial status and remaining paid amount correct. | P1 | Refund | Functional | Not Run
PAY-064 | Refund failure/retry | Refund available | Force refund failure then retry. | Provider refund failure | No false Refunded; retry/audit trail available. | P1 | Refund | Functional | Not Run
PAY-070 | Session | Expired checkout before payment | Create checkout; wait expiry | Attempt payment after expiry. | Expired session | Rejected or refreshed; no stale charge. | P0 | Expiry | Not Run
PAY-071 | Session | Price changes after checkout | QA price fixture | Change price after checkout; pay. | Changed room/package price | Server revalidates; confirmation required; no stale charge. | P0 | Concurrency | Not Run
PAY-072 | Concurrency | Two users pay last available room | One room available | Submit payments concurrently. | Two QA users | Only one booking succeeds; other receives safe failure/refund path. | P0 | Concurrency | Not Run
PAY-073 | Concurrency | Multiple callbacks concurrent | Webhook endpoint | Send same event concurrently. | Same event ID | Atomic idempotency; one update only. | P0 | Concurrency | Not Run
PAY-080 | Privacy | Sensitive data masking | Payment flow executed | Inspect UI, API, logs, analytics and receipt. | Card/CVV/OTP test values | No full card, CVV, password or OTP stored/logged/exposed. | P0 | Security | Not Run
PAY-081 | Audit | Transaction audit trail | Payment outcome available | Trace checkout, payment, webhook, booking and refund IDs. | Correlation IDs | Complete searchable audit trail with timestamps and actors. | P1 | Observability | Not Run
PAY-082 | Rate Limit | Repeated payment submit | QA account/sandbox | Submit same payment repeatedly within short interval. | Repeated request | Rate limit/idempotency prevents duplicate charge. | P1 | Security | Not Run
PAY-083 | Accessibility | Payment error/success messaging | Payment UI open | Keyboard navigate, inspect labels/focus and error messages. | Invalid/success methods | Errors are visible, associated with fields, readable and keyboard accessible. | P2 | Accessibility | Not Run

## Bug Examples
Bug ID | Example Title | Expected | Actual | Severity | Priority | Recommended Evidence
BUG-PAY-001 | Payment success but booking remains Pending | Successful gateway callback updates booking to Paid/Confirmed | Gateway transaction success but booking remains Pending after SLA | Critical | P0 | Gateway response, webhook payload/signature, booking record, correlation ID
BUG-PAY-002 | Cancelled payment marked as Paid | Cancel callback keeps booking unpaid | User cancels at gateway but booking/receipt shows Paid | Critical | P0 | Cancel response, callback, UI screenshot, transaction ID
BUG-PAY-003 | Duplicate callback creates duplicate booking | Replay webhook is idempotent | Same event creates second booking/receipt | Critical | P0 | Two webhook requests, event ID, duplicate booking IDs
BUG-PAY-004 | OTP not delivered after booking verification request | OTP delivered within configured SLA or clear retry state | No SMS received; user cannot continue | Critical | P0 | Phone masked, OTP request ID, provider delivery log, timestamps

## Sandbox Test Data
Data Type | Value/Pattern | Purpose | Source
Success card | Provider official sandbox success card | Successful payment | Payment provider docs
Decline card | Provider official decline card | Generic decline | Payment provider docs
3DS failure | Provider official 3DS failure method | Authentication failure | Payment provider docs
Cancel method | Gateway Cancel/Back flow | Cancellation | Payment provider docs
Timeout method | Provider timeout fixture | Timeout/recovery | Payment provider docs
Webhook secret | Sandbox-only secret | Signature validation | Payment provider config
Test phone | Approved QA phone only | SMS/OTP delivery | QA owner
Test email | qa-payment@example.com | Receipt notification | QA data
Do not use | Real card/CVV/OTP/password | Safety restriction | Mandatory